PAIR Platform

Project Estimation Document

| Project Name | PAIR – TalentBridge Platform |
| --- | --- |
| Document Type | Project Estimation |
| Version | v1.0 |
| Status | Draft – To be reviewed and validated with client/stakeholders |
| Date | April 2026 |

1. Introduction

This document presents the development effort estimates for the PAIR platform. Estimates are derived using expert judgement and analogy-based estimation, which involves comparing features to similar past work and adjusting for complexity (PMBOK, 2021). All estimates are expressed as development day ranges to account for uncertainty in a capstone project context.

The overall development effort is estimated based on the complexity of core features and the 2-month capstone timeframe. Estimates assume a small development team using an iterative development approach.

2. Estimated Effort by Feature

| Feature | Description | Estimated Effort |
| --- | --- | --- |
| User Registration & Authentication (incl. Google OAuth 2.0) | Account creation, login/logout, password reset, Google OAuth integration, role differentiation, consent | 3–4 days |
| Profile Management (Talent & Recruiter) | Profile creation, editing, visibility controls, skills and certification management | 3–4 days |
| Artifact Upload & Management | PDF upload, validation, storage reference, edit/delete, classification categories | 3–4 days |
| Admin Verification Workflow | Pending/Approved/Rejected status management, email notifications to talents | 2–3 days |
| Search & Filtering Functionality | Keyword search, classification filter, name filter, favorites filter, results display | 3–5 days |
| Role-Based Access Control | Talent, Recruiter, and Admin role enforcement across all platform functions | 2–3 days |
| Notification System (incl. individual and delete all) | Interest notifications, storage, duplicate prevention, individual delete, delete all | 3–4 days |
| Project Participants Management | Add by email, registration validation, 7-participant limit, display, profile navigation | 2–3 days |
| AI-Powered Quick Summary Feature | AI button integration, side panel display, structured summary generation from PDF | 2–3 days |
| Azure Infrastructure Setup (Dev/Test and Live environments) | Azure hosting, PostgreSQL setup, Blob Storage, OAuth whitelist, environment separation | 2–3 days |
| Total Estimated Development Effort |  | Approximately 75–80 days |

3. Estimation Notes

Estimates assume a small development team and iterative development approach.

Search, verification, and notification features may require additional testing time.

External integrations and AI-based features beyond Quick Summary are excluded from scope and estimation.

UI refinement and usability testing are included within feature development time.

All estimates are expressed as ranges to reflect inherent uncertainty in early-stage project planning.

4. Project Timeline Overview

The following table provides a high-level timeline overview for the 2-month capstone delivery period.

| Phase | Activities | Duration |
| --- | --- | --- |
| Phase 1 – Requirements & Planning | BRD, stakeholder analysis, user stories, use cases, solution architecture | Week 1–2 |
| Phase 2 – Core Development | Authentication, profile management, artifact upload, admin verification, RBAC | Week 2–4 |
| Phase 3 – Feature Development | Search & filtering, notifications, participants, Quick Summary, Azure setup | Week 4–6 |
| Phase 4 – Testing | Functional testing, defect resolution, UAT | Week 6–7 |
| Phase 5 – Review & Handover | Final documentation, client review, project delivery | Week 7–8 |

References

Project Management Institute. (2021). A guide to the project management body of knowledge (PMBOK Guide) (7th ed.). Project Management Institute.